## Feuil1
# | Priority | REFDES | Modification Description | Reason of Change | Actual | New | Note | Mod Life Cycle | Certification Method | CS-E impact | Production Impact
1 | 1 | U2 | +28Vdc Input Filter replacement | Obsolescence | FN409-13 | Custom Design | Umbra are working on design => W24 | CR | T | Power input EMI Vibration Temeprature others Impacts ? | end of 2018
2 | 1 | U34 | Replacement of Gate Driver for 3-phase bridge transistor | Obsolescence (2017) | IR2336DS | IR2136STR | Document Justification Design is needed and ATP with new component | CDAR | A |  | No impact
3 | 1 | U35 | Add DC Link Overvoltage protection | PR163 | x | M15KP51A | Regenerative energy dissipation circuit on DC link 23/05 : Eng Test in progress 08/06 : Presentation sent to Safran Aircraft Engines | CR | T | TBD
4 | 1 | New | Modification of triggering threshold for Propeller Speed comparator on HW Security | PR161 | x |  | Triggering threshold shall be set at 230rpm Only resistor value modification is requested Functional Test DJD is needed and ATP with new component 08/06 : to verify if we introduce this modification | CDAR | A
5 | 2 | U1 | Main DC/DC converter replacement | Operative temperature | GAIA MGDS-10-J-F/T | Synqor MQBL-28-15S | Synqor is a USA based company Synqor max temp is 125°C Gaia max temp is 105°C Umbra : - potential export issue --> to validate with EPI/Airbus to use Synqor manufacturer, perfomance is better then Gaia (temperature) => Validate the ECC pdf - cost of the unit 08/06 : Decision for export issue ? | CR | T | Power input EMI Temperature
6 | 3 | U16 | Replacement of DC/DC converter for CAN bus power supply (+5Vdc) | PR165 | Traco TES2N | Linear LTM8046MPY Or equivalent | LTM has BGA Package No Fit Form Function => PCB impact | CR | T | Temperature Vibration others ?
7 | 3 | - U24 / U20 - D2/ D3 - C6, C7, C8, C43, C26,C42, C17 - C12 - R110 & R11 & U22 | - Instability of Operational Amplfiers in some usages - 2 diodes in parallel - some electronics components are overstressed + Tatalum capacitors + Amuminium capacitors - Minor error in schematics | Reliability and Design maturity improvement |  |  | - 2 diodes in parallel => Schematic symbol could be more clear | CDAR | A
8 | 3 | F2 | Input Fuse | Reliability and Design maturity improvement | SSQ10 | DELETED |  | CDAR | A
9 | 2 | U7, U9 | Design error on discrete interface (SVOA & SVOB) | Reliability and Design maturity improvement |  |  |  | CDAR | A
10 | 1 | New | Thermal limitation of PBCU | Reliability and Design maturity improvement | x | Thermal Stamp | 08/06 Thermal Stamp : proposal msut be done by Safran Aircraft Engines | Thermal Stamp : TBD ? | T | TBD
voltage reference
linear 1074HT
Note on K2: T = Test A = Analysis NA = Not Applicable
Note on H3: Define a new component to define Mod Life Cycle
Note on K6: With functional Test
Note on H8: Define a new component to define Mod Life Cycle Traco : SMD-package LTM8046 : BGA package Could you define a new equivalent component with SMD package to indroduce by CDAR. If the packages are differents, the mod will be introduced by CR with a new design (PCB impact).